## Task Tracker
TASK TRACKER
Name: |  |  |  |  | Date:
TASK TITLE | STATUS | PRIORITY | START DATE | DUE DATE | PCT OF TASK COMPLETE | COMMENTS | STATUS MENU | PRIORITY MENU
Researched regarding possible senarios for |  | HIGH |  |  | 0% | It was very difficult for us to find the scenario, finally we got one language scenario and rating . | ☐ | HIGH
the music database | ☒ | MEDIUM | 26/03/2019 | 2019-01-04 | 100% |  | ☒ | MEDIUM
|  | LOW |  |  | 0% |  |  | LOW
0%
Worked on the number of tables that can be | ☒ | HIGH | 2019-01-04 | 2019-03-04 | 100% | we have discussed every possible outcome of the table and at the end we came up with seven tables in our database
included in the database |  | MEDIUM |  |  | 0%
|  | LOW |  |  | 0%
0%
Worked on the entities and their attributes |  | HIGH |  |  | 0%
that is required for all tables | ☒ | MEDIUM | 2019-04-04 | 2019-04-04 | 100% | We worked on this faster than expected and achieved the task faster than expected.
|  | LOW |  |  | 0%
0%
|  | HIGH |  |  | 0%
Relationships between tables | ☒ | MEDIUM | 2019-04-04 | 2019-06-04 | 100% | We have done many relationship with seven tables respectively to achieve 3rd normal form(i.e 3NF)
|  | LOW |  |  | 0%
0%
Constructed an ER diagram | ☒ | HIGH | 2019-06-04 | 2019-08-04 | 100% | It took long than expexted, because there are several results we have to keep in mind before constructing ER diagram.
|  | MEDIUM |  |  | 0%
|  | LOW |  |  | 0%
0%
Inserted and tested values for all the tables | ☒ | HIGH | 2019-08-04 | 2019-09-04 | 100% | we discussed the numerous values and inserted them accordingly
in the database |  | MEDIUM |  |  | 0%
|  | LOW |  |  | 0%
0%
Discussed about the queries that can be | ☒ | HIGH | 2019-10-04 | 2019-10-04 | 100% | we discussed all the possible queries we can create based on our 2 scenario, finally we ended up getting four good queries.
created based on the senario |  | MEDIUM |  |  | 0%
|  | LOW |  |  | 0%
0%
Worked on all the seven queries | ☒ | HIGH | 2019-10-04 | 2019-14-04 | 100% | we divided queries accordingly and worked on them individually.
|  | MEDIUM |  |  | 0%
|  | LOW |  |  | 0%
0%
Worked on the queries of the senario | ☒ | HIGH | 2019-14-04 | 2019-14-04 | 100% | we did many meeting for this scenario and achieved that succesfully.
|  | MEDIUM |  |  | 0%
|  | LOW |  |  | 0%
0%
Documentation report preparation | ☒ | HIGH | 2019-14-04 | 2019-15-04 | 100% | we did many meeting for the technical report as it contains many documention. We discussed all the scenario , queries,script,model files to create detailed report based on our project.
|  | MEDIUM |  |  | 0%
|  | LOW |  |  | 0%
100%